## user story and ac
List of User Stories
S.N. | Features | Acceptance Criteria | User story
1 | Secure Login and User Identity Management | • Users can register using email/phone and password. • Users can log in securely with valid credentials. • System asks for full name, phone number, email, and location access. • System shows notification if login is unsuccessful. • System takes user to home page after successful login. | As a user, I want to log in securely using my credentials so that I can access my account, join groups, and use the app features.
2 | Dynamic Budget Split | • System calculates total shared cost correctly. • System splits cost among users fairly. • Final split amount is shown for each user. | As a user, I want the app to fairly split shared costs so that everyone pays correctly.
3 | Ride Cost Estimation | • System calculates distance between user and meeting point. • System estimates ride cost based on distance. • Shows cost separately for each user. • Updates cost when location changes. | .As a user, I want to see ride cost estimates so that I can plan my travel.
4 | Emergency Alerts | • SOS button is clearly accessible in the app. • Sends live location to emergency contacts. • Logs alert timestamp for review. • Cancel with PIN after false trigger. | As a user, I want an emergency alert system so that I can quickly contact help if needed
5 | Meeting Reminder | • User can set meeting date and time. • System sends notifications before the meeting. • Reminder includes meeting location details. • Users can edit or delete reminders. | As a user, I want reminders for meetings so that I don’t miss them
6 | Group Voting Place | • System shows list of meeting place options. • Users can vote for one option. • Final place selected based on highest votes. • In case of a draw, the poll is restarted. | As a user, I want to vote for meeting places so that the group can decide easily.
7 | Midpoint Meeting Calculator | • System calculates a midpoint using all user locations. • The midpoint is displayed on the map. • The midpoint updates when locations change. | As a user, I want a fair midpoint location so everyone travels a similar distance.
8 | Nearby Restaurant Recommendation | • Restaurants near the midpoint are displayed. • Recommendations show rating, distance, and price range. • Users can filter by category or budget. • Option to add restaurant to the Group Voting Place list. | As a user, I want restaurant suggestions near the meeting point for convenience.
9 | User Profile Management | • Profile data is only accessible after login. • Users can view and edit their profile details. • Users can save preferences (budget, cuisine, transport). • Users can access meetup history and saved places. | As a user, I want to view and update my profile so that I can manage my personal details, preferences, and activity history.
10 | Fare Drop Alert | • App displays estimated percentage fare drop. • Push notification sent when fare drops. • Minimum drop threshold setting available. • Dismiss alerts if not needed. | As a user, I want to receive predictions about fare drops to book rides at the lowest possible price.
11 | Ambience-Based Restaurant Filter | • Users can select ambience categories (casual, family-friendly, fine dining). • System displays only restaurants matching selected ambience tags. • Multiple ambience filters can be applied simultaneously. • Applied filters are visibly active and removable. • Results update dynamically without full page reload. • Clear empty-state message shown if no matches found. | As a user, I want to filter restaurant suggestions by ambience.
12 | Group Chat for Meetup Planning | • Users can create a group chat linked to a restaurant or plan. • Users can invite participants via app or shareable link. • Participants can send, receive, and view messages in real time. • Users can share restaurant options within the chat. • Messages display timestamps and sender identification. • Notifications are sent for new messages. • Users can leave or mute the group chat. • Chat history persists and is accessible to all participants. | As a user, I want to chat with group members so that we can plan the meetup easily.
13 | Restaurant Rating & Review Filter | • Users can filter restaurants by rating range. • Users can sort results by highest rating or most reviewed. • Reviews display rating, text, and reviewer details. • System excludes restaurants below selected rating thresholds. • Filter changes update results instantly. • Fallback message appears when no restaurants match criteria. | As a user, I want to filter places by ratings so that I can choose better options.
14 | Cuisine Preference Selection | • Users can search and select multiple cuisines. • System filters results based on intersection of selected cuisines. • Organizer can override group cuisine preferences. • System suggests similar cuisines based on selected preferences. | As a user, I want to select cuisine preferences so that I get relevant suggestions.
15 | Budget-Based Restaurant Filter | • System displays and updates group's average budget in real time. • Each restaurant shows estimated cost per person. • Restaurants over budget are hidden or clearly marked with a warning. • Users can adjust budget using a visual scale. • Results update instantly based on selected budget. | As a user, I want to filter places by budget so that I stay within my limit.
16 | Walking Distance Calculator | • Current location can be auto-detected or entered manually. • Destination can be searched or selected on the map. • Walking distance between both points is displayed. • Distance shown clearly in kilometers or meters. | As a user, I want to enter my current location and destination so that I can calculate the walking distance between them.
17 | Language Translation- English/Nepali | • Chat messages include a translate option. • Clicking translate shows the message in the selected language. • Original message remains visible along with the translated text. • Translation works for both sent and received messages. | As a user, I want messages in chat to be automatically translated to my preferred language.
18 | Meetup Gallery | • Attendees can upload photos during and after the meetup. • Photos are auto-sorted by time and can be manually rearranged. • Users can like and comment on individual photos. • Photos can be downloaded. | As a user, I want a shared photo gallery for each meetup so that we can collect and relive memories together.
19 | Achievement/Badge system | • Badges are awarded based on meetup and chat frequency between two users. • Interaction count is tracked for each user pair. • Badge is unlocked when a specific interaction threshold is reached. • Earned badges are shown in both users' profiles. | As a user, I want to earn badges when I frequently meet or talk with another user so that my meaningful connections are rewarded.
20 | Peak Hour Fare Warning | • Peak hours are identified based on predefined time ranges or live demand. • A warning is shown when user selects a ride during peak hours. • The warning clearly mentions fares may be higher than usual. • Warning appears before the user confirms the ride. | As a user, I want to be informed when fares are high during peak hours so that I can plan my travel at a cheaper time.
21 | Favorite Places Save Option | • Open a place detail and tap heart/bookmark to save or unsave. • View saved places in the Saved list. • Create or assign saved places to a custom list. • Select a saved place when creating a meetup. • Access saved places offline. | As a user, I want to save places so I can quickly reuse them when planning meetups.
22 | Smart Notification Alerts | • Enable/disable alert types and channels in meetup settings. • Receive scheduled reminders (departure, arrival, start). • Receive 'leave now' alerts based on real-time traffic/transit. • Related notifications are grouped by meetup. | As a user, I want smart alerts so I get timely, useful reminders for meetups.
23 | Restaurant Offers Check | • View active offers with validity dates on restaurant detail page. • Opt in to receive offer expiry reminders. • Apply or save an offer to use at checkout. • Expired offers are hidden or marked inactive. | As a user, I want to see current offers so I can save money at events and restaurants.
24 | Meeting History & Analytics | • End or archive a meetup (automatic on completion). • View past meetups in reverse-chronological order. • Search and filter meetings by date, place, or attendee. • Open a meeting to view basic analytics (attendance, duration). • Add notes or export a meeting record if needed. | As a user, I want to view past meetings so I can track attendance and activity over time.
25 | Multi-Stop Route Planning | • Add, remove, or reorder stops in a route. • Request route calculation and view full path on the map. • Choose optimised path by time or distance and review ETA. • Save or share the multi-stop route and start navigation. | As a user, I want to create routes with multiple stops so we can pick up everyone efficiently.
26 | Friend Availability Scheduler | • Set available time slots and invite/select friends. • View shared calendar with common free time highlighted. • Choose a suitable time and confirm meetup. • Receive notification after confirmation. | As a user, I want to see availability so that I can plan better.
27 | Rating & feedback system | • Open completed meetup or place detail. • Submit a star rating and written feedback. • Feedback is linked to the relevant place or service. • Submitted feedback is visible to other users. | As a user, I want to give feedback so that services improve.
28 | Dark/light mode | • Open settings and select theme option. • Choose dark or light mode. • Enable auto mode based on system preference (optional). • Preference is saved and applied across sessions. | As a user, I want theme options so that I can use the app comfortably.
29 | Calendar sync | • Connect external calendar with user permission. • Import and export meetup events. • Real-time sync between app and calendar. • Detect scheduling conflicts. • Secure data handling and multi-account support. | As a user, I want to sync meetings so that I manage time easily.
30 | "Explore" feed of trending meetup spots | • Open Explore section and scroll through trending places. • View place details, ratings, and map location. • Search and filter places by category. • Like or save a place and share with friends. | As a user, I want to explore trending meetup spots so that I can discover popular places easily.
2

## user stories wo priority hierar
Feature ID | Feature Name | User Story ID | Priority | As a <Type of User> | I need to <perform some task> | So that I can <achieve something> | Acceptance Criteria
F1 | Secure Login & User Identity Management | 1.1 | High | User | register to the system by creating an account | I can use the system | • Add register button in the navigation bar. • Display the registration form when button is clicked. • System asks for full name, phone number, email, and location access. • Provide all required fields with proper validation. • Click the register button to create the account.
|  | 1.2 | High | User | be notified via an email verification mail to my email address | I can verify my account after registration | • Send an email verification link to the registered email address. • Click the verification link for account verification. • Verification link expires after 24 hours. • Once verified, link cannot be reused.
|  | 1.3 | High | User | login to the system after registration | I can access the system | • Add a login button in the navigation bar. • Display the login form when button is clicked. • Provide login credentials with validation. • Click the login button for accessing the system. • Display the home page after successful login. • Show notification if login is unsuccessful.
|  | 1.4 | High | User | reset my password | I can create a new one to access the system | • Add a forget password button on the login page. • Display the form for resetting the password. • Accept valid and registered email and submit it. • Send a password reset link to the provided email address. • Access the password reset form and provide the new password. • Reset link expires after 24 hours. • Once verified, link cannot be reused.
F2 | Dynamic Budget Split | 2.1 | Low | User | split shared costs fairly among all group members | I can ensure everyone pays the correct amount | • System calculates total shared cost correctly. • System splits cost among users fairly. • Final split amount is shown for each user.
F3 | Ride Cost Estimation | 3.1 | High | User | see ride cost estimates based on my location and the meeting point | I can plan my travel budget in advance | • System calculates distance between user and meeting point. • System estimates ride cost based on distance. • Shows cost separately for each user. • Updates cost when location changes.
F4 | Emergency Alerts | 4.1 | High | User | trigger an emergency alert using a single SOS button | I can quickly contact help if needed | • SOS button is clearly accessible in the app. • Sends live location to emergency contacts. • Logs alert timestamp for review. • Cancel with PIN after false trigger.
F5 | Meeting Reminder | 5.1 | Medium | User | set and receive reminders for upcoming meetings | I don't miss my scheduled meetups | • User can set meeting date and time. • System sends notifications before the meeting. • Reminder includes meeting location details. • Users can edit or delete reminders.
F6 | Group Voting Place | 6.1 | Medium | User | vote for a preferred meeting place from a group list | the group can decide on a location easily | • System shows list of meeting place options. • Users can vote for one option. • Final place selected based on highest votes. • In case of a draw, the poll is restarted.
F7 | Midpoint Meeting Calculator | 7.1 | High | User | calculate a fair midpoint location based on all user locations | everyone travels a similar distance to the meeting point | • System calculates a midpoint using all user locations. • The midpoint is displayed on the map. • The midpoint updates when locations change.
F8 | Nearby Restaurant Recommendation | 8.1 | Medium | User | view nearby restaurant recommendations near the meeting midpoint | I can find a convenient place to meet | • Restaurants near the midpoint are displayed. • Recommendations show rating, distance, and price range. • Users can filter by category or budget. • Option to add restaurant to the Group Voting Place list.
F9 | User Profile Management | 9.1 | High | User | view and update my profile details and preferences | I can manage my personal information and activity history | • Profile data is only accessible after login. • Users can view and edit their profile details. • Users can save preferences (budget, cuisine, transport). • Users can access meetup history and saved places.
F10 | Fare Drop Alert | 10.1 | Medium | User | receive predictions and alerts about fare drops | I can book rides at the lowest possible price | • App displays estimated percentage fare drop. • Push notification sent when fare drops. • Minimum drop threshold setting available. • Dismiss alerts if not needed.
F11 | Ambience-Based Restaurant Filter | 11.1 | Low | User | filter restaurant suggestions by ambience type | I can find places that match the group mood | • Users can select ambience categories (romantic, casual, family-friendly, fine dining). • System displays only restaurants matching selected ambience tags. • Multiple ambience filters can be applied simultaneously. • Applied filters are visibly active and removable. • Results update dynamically without full page reload. • Clear empty-state message shown if no matches found.
F12 | Group Chat for Meetup Planning | 12.1 | Low | User | create and use a group chat linked to a meetup plan | we can coordinate and plan the meetup easily | • Users can create a group chat linked to a restaurant or plan. • Users can invite participants via app or shareable link. • Participants can send, receive, and view messages in real time. • Users can share restaurant options within the chat. • Messages display timestamps and sender identification. • Notifications are sent for new messages. • Users can leave or mute the group chat. • Chat history persists and is accessible to all participants.
F13 | Restaurant Rating & Review Filter | 13.1 | Medium | User | filter places by rating range and sort by highest rated | I can choose better dining options | • Users can filter restaurants by rating range. • Users can sort results by highest rating or most reviewed. • Reviews display rating, text, and reviewer details. • System excludes restaurants below selected rating thresholds. • Filter changes update results instantly. • Fallback message appears when no restaurants match criteria.
F14 | Cuisine Preference Selection | 14.1 | Medium | User | select and save cuisine preferences for restaurant filtering | I get relevant and personalized restaurant suggestions | • Users can search and select multiple cuisines. • System filters results based on intersection of selected cuisines. • Organizer can override group cuisine preferences. • System suggests similar cuisines based on selected preferences.
F15 | Budget-Based Restaurant Filter | 15.1 | Medium | User | filter restaurants based on the group's average budget | I stay within my spending limit | • System displays and updates group's average budget in real time. • Each restaurant shows estimated cost per person. • Restaurants over budget are hidden or clearly marked with a warning. • Users can adjust budget using a visual scale. • Results update instantly based on selected budget.
F16 | Walking Distance Calculator | 16.1 | Low | User | enter my current location and destination to calculate walking distance | I can estimate the effort needed to reach the meeting point on foot | • Current location can be auto-detected or entered manually. • Destination can be searched or selected on the map. • Walking distance between both points is displayed. • Distance shown clearly in kilometers or meters.
F17 | Language Translation (English/Nepali) | 17.1 | Low | User | translate chat messages between English and Nepali | I can communicate in my preferred language | • Chat messages include a translate option. • Clicking translate shows the message in the selected language. • Original message remains visible along with the translated text. • Translation works for both sent and received messages.
F18 | Meetup Gallery | 18.1 | Low | User | upload and view photos in a shared meetup gallery | we can collect and relive memories from our meetups | • Attendees can upload photos during and after the meetup. • Photos are auto-sorted by time and can be manually rearranged. • Users can like and comment on individual photos. • Photos can be downloaded.
F19 | Achievement / Badge System | 19.1 | Low | User | earn badges based on frequency of meetups and interactions with other users | my meaningful connections are recognized and rewarded | • Badges are awarded based on meetup and chat frequency between two users. • Interaction count is tracked for each user pair. • Badge is unlocked when a specific interaction threshold is reached. • Earned badges are shown in both users' profiles.
F20 | Peak Hour Fare Warning | 20.1 | Medium | User | receive a warning when ride fares are high during peak hours | I can plan my travel at a cheaper time | • Peak hours are identified based on predefined time ranges or live demand. • A warning is shown when user selects a ride during peak hours. • The warning clearly mentions fares may be higher than usual. • Warning appears before the user confirms the ride.
F21 | Favourite Places Save Option | 21.1 | Low | User | save and organise favourite places for quick reuse in meetup planning | I can quickly reuse preferred locations when planning meetups | • Open a place detail and tap heart/bookmark to save or unsave. • View saved places in the Saved list. • Create or assign saved places to a custom list. • Select a saved place when creating a meetup. • Access saved places offline.
F22 | Smart Notification Alerts | 22.1 | Medium | User | receive smart notifications with timely reminders for meetups | I get useful and relevant alerts without being overwhelmed | • Enable/disable alert types and channels in meetup settings. • Receive scheduled reminders (departure, arrival, start). • Receive 'leave now' alerts based on real-time traffic/transit. • Related notifications are grouped by meetup.
F23 | Restaurant Offers Check | 23.1 | Low | User | view current offers at restaurants and events | I can save money when dining out | • View active offers with validity dates on restaurant detail page. • Opt in to receive offer expiry reminders. • Apply or save an offer to use at checkout. • Expired offers are hidden or marked inactive.
F24 | Meeting History & Analytics | 24.1 | Medium | User | view past meeting history with attendance and activity analytics | I can track attendance and review group activity over time | • End or archive a meetup (automatic on completion). • View past meetups in reverse-chronological order. • Search and filter meetings by date, place, or attendee. • Open a meeting to view basic analytics (attendance, duration). • Add notes or export a meeting record if needed.
F25 | Multi-Stop Route Planning | 25.1 | Medium | User | create routes with multiple stops to pick up group members | we can coordinate group travel with minimal detours | • Add, remove, or reorder stops in a route. • Request route calculation and view full path on the map. • Choose optimised path by time or distance and review ETA. • Save or share the multi-stop route and start navigation.
F26 | Friend Availability Scheduler | 26.1 | Medium | User | view friends' availability and identify common free time slots | I can plan meetups at a time that works for everyone | • Set available time slots and invite/select friends. • View shared calendar with common free time highlighted. • Choose a suitable time and confirm meetup. • Receive notification after confirmation.
F27 | Rating & Feedback System | 27.1 | Low | User | submit ratings and feedback for meetup places and services | services and recommendations can be improved over time | • Open completed meetup or place detail. • Submit a star rating and written feedback. • Feedback is linked to the relevant place or service. • Submitted feedback is visible to other users.
F28 | Dark / Light Mode | 28.1 | Low | User | switch between dark and light mode in app settings | I can use the app comfortably in different lighting conditions | • Open settings and select theme option. • Choose dark or light mode. • Enable auto mode based on system preference (optional). • Preference is saved and applied across sessions.
F29 | Calendar Sync | 29.1 | Low | User | sync my external calendar with the app | I can manage my time easily without switching between apps | • Connect external calendar with user permission. • Import and export meetup events. • Real-time sync between app and calendar. • Detect scheduling conflicts. • Secure data handling and multi-account support.
F30 | Explore Feed of Trending Meetup Spots | 30.1 | Low | User | browse an Explore feed of trending and popular meetup spots | I can discover popular places easily | • Open Explore section and scroll through trending places. • View place details, ratings, and map location. • Search and filter places by category. • Like or save a place and share with friends.

## user stories w priority hierarc
Feature ID | Feature Name | User Story ID | Priority | As a <Type of User> | I need to <perform some task> | So that I can <achieve something> | Acceptance Criteria
F1 | Secure Login & User Identity Management | 1.1 | High | User | register to the system by creating an account | I can use the system | • Add register button in the navigation bar. • Display the registration form when button is clicked. • System asks for full name, phone number, email, and location access. • Provide all required fields with proper validation. • Click the register button to create the account.
|  | 1.2 | High | User | be notified via an email verification mail to my email address | I can verify my account after registration | • Send an email verification link to the registered email address. • Click the verification link for account verification. • Verification link expires after 24 hours. • Once verified, link cannot be reused.
|  | 1.3 | High | User | login to the system after registration | I can access the system | • Add a login button in the navigation bar. • Display the login form when button is clicked. • Provide login credentials with validation. • Click the login button for accessing the system. • Display the home page after successful login. • Show notification if login is unsuccessful.
|  | 1.4 | High | User | reset my password | I can create a new one to access the system | • Add a forget password button on the login page. • Display the form for resetting the password. • Accept valid and registered email and submit it. • Send a password reset link to the provided email address. • Access the password reset form and provide the new password. • Reset link expires after 24 hours. • Once verified, link cannot be reused.
F3 | Ride Cost Estimation | 3.1 | High | User | see ride cost estimates based on my location and the meeting point | I can plan my travel budget in advance | • System calculates distance between user and meeting point. • System estimates ride cost based on distance. • Shows cost separately for each user. • Updates cost when location changes.
F4 | Emergency Alerts | 4.1 | High | User | trigger an emergency alert using a single SOS button | I can quickly contact help if needed | • SOS button is clearly accessible in the app. • Sends live location to emergency contacts. • Logs alert timestamp for review. • Cancel with PIN after false trigger.
F7 | Midpoint Meeting Calculator | 7.1 | High | User | calculate a fair midpoint location based on all user locations | everyone travels a similar distance to the meeting point | • System calculates a midpoint using all user locations. • The midpoint is displayed on the map. • The midpoint updates when locations change.
F9 | User Profile Management | 9.1 | High | User | view and update my profile details and preferences | I can manage my personal information and activity history | • Profile data is only accessible after login. • Users can view and edit their profile details. • Users can save preferences (budget, cuisine, transport). • Users can access meetup history and saved places.
F5 | Meeting Reminder | 5.1 | Medium | User | set and receive reminders for upcoming meetings | I don't miss my scheduled meetups | • User can set meeting date and time. • System sends notifications before the meeting. • Reminder includes meeting location details. • Users can edit or delete reminders.
F6 | Group Voting Place | 6.1 | Medium | User | vote for a preferred meeting place from a group list | the group can decide on a location easily | • System shows list of meeting place options. • Users can vote for one option. • Final place selected based on highest votes. • In case of a draw, the poll is restarted.
F8 | Nearby Restaurant Recommendation | 8.1 | Medium | User | view nearby restaurant recommendations near the meeting midpoint | I can find a convenient place to meet | • Restaurants near the midpoint are displayed. • Recommendations show rating, distance, and price range. • Users can filter by category or budget. • Option to add restaurant to the Group Voting Place list.
F10 | Fare Drop Alert | 10.1 | Medium | User | receive predictions and alerts about fare drops | I can book rides at the lowest possible price | • App displays estimated percentage fare drop. • Push notification sent when fare drops. • Minimum drop threshold setting available. • Dismiss alerts if not needed.
F13 | Restaurant Rating & Review Filter | 13.1 | Medium | User | filter places by rating range and sort by highest rated | I can choose better dining options | • Users can filter restaurants by rating range. • Users can sort results by highest rating or most reviewed. • Reviews display rating, text, and reviewer details. • System excludes restaurants below selected rating thresholds. • Filter changes update results instantly. • Fallback message appears when no restaurants match criteria.
F14 | Cuisine Preference Selection | 14.1 | Medium | User | select and save cuisine preferences for restaurant filtering | I get relevant and personalized restaurant suggestions | • Users can search and select multiple cuisines. • System filters results based on intersection of selected cuisines. • Organizer can override group cuisine preferences. • System suggests similar cuisines based on selected preferences.
F15 | Budget-Based Restaurant Filter | 15.1 | Medium | User | filter restaurants based on the group's average budget | I stay within my spending limit | • System displays and updates group's average budget in real time. • Each restaurant shows estimated cost per person. • Restaurants over budget are hidden or clearly marked with a warning. • Users can adjust budget using a visual scale. • Results update instantly based on selected budget.
F20 | Peak Hour Fare Warning | 20.1 | Medium | User | receive a warning when ride fares are high during peak hours | I can plan my travel at a cheaper time | • Peak hours are identified based on predefined time ranges or live demand. • A warning is shown when user selects a ride during peak hours. • The warning clearly mentions fares may be higher than usual. • Warning appears before the user confirms the ride.
F24 | Meeting History & Analytics | 24.1 | Medium | User | view past meeting history with attendance and activity analytics | I can track attendance and review group activity over time | • End or archive a meetup (automatic on completion). • View past meetups in reverse-chronological order. • Search and filter meetings by date, place, or attendee. • Open a meeting to view basic analytics (attendance, duration). • Add notes or export a meeting record if needed.
F25 | Multi-Stop Route Planning | 25.1 | Medium | User | create routes with multiple stops to pick up group members | we can coordinate group travel with minimal detours | • Add, remove, or reorder stops in a route. • Request route calculation and view full path on the map. • Choose optimised path by time or distance and review ETA. • Save or share the multi-stop route and start navigation.
F26 | Friend Availability Scheduler | 26.1 | Medium | User | view friends' availability and identify common free time slots | I can plan meetups at a time that works for everyone | • Set available time slots and invite/select friends. • View shared calendar with common free time highlighted. • Choose a suitable time and confirm meetup. • Receive notification after confirmation.
F2 | Dynamic Budget Split | 2.1 | Low | User | split shared costs fairly among all group members | I can ensure everyone pays the correct amount | • System calculates total shared cost correctly. • System splits cost among users fairly. • Final split amount is shown for each user.
F11 | Ambience-Based Restaurant Filter | 11.1 | Low | User | filter restaurant suggestions by ambience type | I can find places that match the group mood | • Users can select ambience categories (romantic, casual, family-friendly, fine dining). • System displays only restaurants matching selected ambience tags. • Multiple ambience filters can be applied simultaneously. • Applied filters are visibly active and removable. • Results update dynamically without full page reload. • Clear empty-state message shown if no matches found.
F12 | Group Chat for Meetup Planning | 12.1 | Low | User | create and use a group chat linked to a meetup plan | we can coordinate and plan the meetup easily | • Users can create a group chat linked to a restaurant or plan. • Users can invite participants via app or shareable link. • Participants can send, receive, and view messages in real time. • Users can share restaurant options within the chat. • Messages display timestamps and sender identification. • Notifications are sent for new messages. • Users can leave or mute the group chat. • Chat history persists and is accessible to all participants.
F16 | Walking Distance Calculator | 16.1 | Low | User | enter my current location and destination to calculate walking distance | I can estimate the effort needed to reach the meeting point on foot | • Current location can be auto-detected or entered manually. • Destination can be searched or selected on the map. • Walking distance between both points is displayed. • Distance shown clearly in kilometers or meters.
F17 | Language Translation (English/Nepali) | 17.1 | Low | User | translate chat messages between English and Nepali | I can communicate in my preferred language | • Chat messages include a translate option. • Clicking translate shows the message in the selected language. • Original message remains visible along with the translated text. • Translation works for both sent and received messages.
F18 | Meetup Gallery | 18.1 | Low | User | upload and view photos in a shared meetup gallery | we can collect and relive memories from our meetups | • Attendees can upload photos during and after the meetup. • Photos are auto-sorted by time and can be manually rearranged. • Users can like and comment on individual photos. • Photos can be downloaded.
F19 | Achievement / Badge System | 19.1 | Low | User | earn badges based on frequency of meetups and interactions with other users | my meaningful connections are recognized and rewarded | • Badges are awarded based on meetup and chat frequency between two users. • Interaction count is tracked for each user pair. • Badge is unlocked when a specific interaction threshold is reached. • Earned badges are shown in both users' profiles.
F21 | Favourite Places Save Option | 21.1 | Low | User | save and organise favourite places for quick reuse in meetup planning | I can quickly reuse preferred locations when planning meetups | • Open a place detail and tap heart/bookmark to save or unsave. • View saved places in the Saved list. • Create or assign saved places to a custom list. • Select a saved place when creating a meetup. • Access saved places offline.
F23 | Restaurant Offers Check | 23.1 | Low | User | view current offers at restaurants and events | I can save money when dining out | • View active offers with validity dates on restaurant detail page. • Opt in to receive offer expiry reminders. • Apply or save an offer to use at checkout. • Expired offers are hidden or marked inactive.
F27 | Rating & Feedback System | 27.1 | Low | User | submit ratings and feedback for meetup places and services | services and recommendations can be improved over time | • Open completed meetup or place detail. • Submit a star rating and written feedback. • Feedback is linked to the relevant place or service. • Submitted feedback is visible to other users.
F28 | Dark / Light Mode | 28.1 | Low | User | switch between dark and light mode in app settings | I can use the app comfortably in different lighting conditions | • Open settings and select theme option. • Choose dark or light mode. • Enable auto mode based on system preference (optional). • Preference is saved and applied across sessions.
F29 | Calendar Sync | 29.1 | Low | User | sync my external calendar with the app | I can manage my time easily without switching between apps | • Connect external calendar with user permission. • Import and export meetup events. • Real-time sync between app and calendar. • Detect scheduling conflicts. • Secure data handling and multi-account support.
F30 | Explore Feed of Trending Meetup Spots | 30.1 | Low | User | browse an Explore feed of trending and popular meetup spots | I can discover popular places easily | • Open Explore section and scroll through trending places. • View place details, ratings, and map location. • Search and filter places by category. • Like or save a place and share with friends.

## User Story Map Board
Legend : US - User Story | RELEASE THEME: Bhetamल
The Backbone | Epic 1 | Epic 2 | Epic 3 | Epic 4 | Epic 5
Flesh on the backbone | Rides & Navigation | Social & Group Meetup | Restaurant Discovery | User Experience & Profile | Smart Alerts & Planning
Sprint / Iteration 1 (19/05/2026-26/05/2026) |  |  |  | US 1 - Secure Login & User Identity Management
SEQUENCE |  |  |  | US 9 - User Profile Management
Version 1.0 |  |  | US 8 - Nearby Restaurant Recommendation
US 4 - Emergency Alerts
Sprint / Iteration 2 (27/05/2026-08/06/2026) | US 3 - Ride Cost Estimation
Version 2.0 | US 2 - Dynamic Budget Split |  | US 14 - Cuisine Preference Selection |  | US 22 - Smart Notification Alerts
US 7 - Midpoint Meeting Calculator
|  | US 6 - Group Voting Place |  | US 28 - Dark / Light Mode
Sprint / Iteration 3 (9/6/2026-17/06/2026) | US 25 - Multi-Stop Route Planning
Version 3.0 |  | US 5 - Meeting Reminder | US 11 - Ambience-Based Restaurant Filter
US 20 - Peak Hour Fare Warning
US 26 - Friend Availability Scheduler
Sprint / Iteration 4 (18/06/2026-27/06/2026) |  |  |  |  | US 29 - Calendar Sync
Version 4.0 |  | US 12 - Group Chat for Meetup Planning |  | US 19 - Achievement / Badge System
| US 10 - Fare Drop Alert |  | US 13 - Restaurant Rating & Review Filter
|  | US 18 - Meetup Gallery | US 15 - Budget-Based Restaurant Filter
Sprint / Iteration 5 (28/06/2026-08/07/2026)
Version 5.0 | US 16 - Walking Distance Calculator | US 24 - Meeting History & Analytics |  | US 17 - Language Translation (English/Nepali) | US 21 - Favourite Places Save Option
|  | US 30 - Explore Feed of Trending Meetup Spots | US 23 - Restaurant Offers Check | US 27 - Rating & Feedback System

## AGILE RELEASE PLAN
At Risk | Development Order | Sprint | Feature ID | Feature Name | Feature Type | Story Points | Assigned Role | Suggested Branch | Start Date | Finish Date | Duration(Hours) | Dependencies | Status | Release Date
| 1 | 1 | US 1 | Secure Login & User Identity Management | Security | 3 | Auth Developer | auth-system | 19/05/2026 | 21/05/2026 | 12 | None | Done
| 2 | 1 | US 9 | User Profile Management | User Management | 2 | Auth Developer | auth-system | 22/05/2026 | 23/05/2026 | 12 | US 1 | Done
| 3 | 1 | US 28 | Dark / Light Mode | UI-UX Enhancement | 1 | Frontend Developer | frontend-ui | 19/05/2026 | 19/05/2026 | 6 | Frontend Setup | Done
| 4 | 1 | US 17 | Language Translation (English/Nepali) | Localisation | 2 | Frontend Developer | frontend-ui | 20/05/2026 | 21/05/2026 | 6 | Frontend Setup | Done
| 5 | 1 | US 4 | Emergency Alerts | Notifications and Alerts | 2 | Backend Developer | backend-core | 22/05/2026 | 23/05/2026 | 6 | US 1 | Done
| 6 | 1 | US 26 | Friend Availability Scheduler | Socials/Collaborations | 2 | Scheduling Developer | scheduler-system | 24/05/2026 | 26/05/2026 | 6 | US 1 | Done | 26/05/2026 | 24/5
| 7 | 2 | US 7 | Midpoint Meeting Calculator | Navigation | 3 | Maps Developer | maps-midpoint | 27/05/2026 | 29/05/2026 | 18 | US 26 | Done
| 8 | 2 | US 8 | Nearby Restaurant Recommendation | Recommendations | 1 | Restaurant Developer | restaurant-system | 30/05/2026 | 30/05/2026 | 8 | US 7 | Done
| 9 | 2 | US 15 | Budget-Based Restaurant Filter | Filtering and Preferences | 1 | Restaurant Developer | restaurant-system | 31/05/2026 | 31/05/2026 | 8 | US 8 | Done
| 10 | 2 | US 11 | Ambience-Based Restaurant Filter | Filtering and Preferences | 2 | Restaurant Developer | restaurant-system | 2026-01-06 | 2026-02-06 | 12 | US 8 | Done
| 11 | 2 | US 13 | Restaurant Rating & Review Filter | Filtering and Preferences | 2 | Restaurant Developer | restaurant-system | 2026-03-06 | 2026-04-06 | 12 | US 8 | Done
| 12 | 2 | US 21 | Favourite Places Save Option | Favourites/Saved Items | 1 | Backend Developer | backend-core | 2026-05-06 | 2026-05-06 | 6 | US 8 | Done | 2026-08-06 | 2026-08-06
| 13 | 3 | US 3 | Ride Cost Estimation | Pricing and Payments | 3 | Ride System Developer | ride-system | 2026-06-06 | 2026-08-06 | 18 | US 7 | Pending
| 14 | 3 | US 10 | Fare Drop Alert | Pricing and Payments | 1 | Ride System Developer | ride-system | 2026-09-06 | 2026-09-06 | 6 | US 3 | Pending
| 15 | 3 | US 20 | Peak Hour Fare Warning | Pricing and Payments | 1 | Ride System Developer | ride-system | 2026-10-06 | 2026-10-06 | 6 | US 3 | Pending
| 16 | 3 | US 16 | Walking Distance Calculator | Navigation | 1 | Maps Developer | maps-midpoint | 2026-11-06 | 2026-11-06 | 6 | US 7 | Pending
| 17 | 3 | US 25 | Multi-Stop Route Planning | Navigation | 3 | Maps Developer | maps-midpoint | 2026-12-06 | 14/06/2026 | 18 | US 7 | Pending
| 18 | 3 | US 23 | Restaurant Offers Check | Pricing and Payments | 1 | Restaurant Developer | restaurant-system | 15/06/2026 | 15/06/2026 | 6 | US 8 | Pending | 15/06/2026 | 17/6
| 19 | 4 | US 6 | Group Voting Place | Socials/Collaborations | 2 | Frontend Developer | frontend-ui | 18/06/2026 | 19/06/2026 | 12 | US 8 | Pending
| 20 | 4 | US 12 | Group Chat for Meetup Planning | Socials/Collaborations | 3 | Backend Developer | backend-core | 20/06/2026 | 22/06/2026 | 18 | US 1 | Pending
| 21 | 4 | US 5 | Meeting Reminder | Notifications and Alerts | 1 | Backend Developer | backend-core | 23/06/2026 | 23/06/2026 | 6 | US 12 | Pending
| 22 | 4 | US 22 | Smart Notification Alerts | Notifications and Alerts | 2 | Backend Developer | backend-core | 24/06/2026 | 25/06/2026 | 12 | US 5 | Pending
| 23 | 4 | US 29 | Calendar Sync | Integration | 1 | Scheduling Developer | scheduler-system | 26/06/2026 | 26/06/2026 | 8 | US 5 | Pending | 27/06/2026 | 27/6
| 24 | 5 | US 18 | Meetup Gallery | Socials/Collaborations | 1 | Frontend Developer | frontend-ui | 28/06/2026 | 28/06/2026 | 6 | US 12 | Pending
| 25 | 5 | US 19 | Achievement / Badge System | Gamification | 1 | Frontend Developer | frontend-ui | 29/06/2026 | 29/06/2026 | 8 | User Activity | Pending
| 26 | 5 | US 24 | Meeting History & Analytics | Analytics | 2 | Analytics Developer | analytics-system | 30/06/2026 | 2026-01-07 | 12 | Completed Meetings | Pending
| 27 | 5 | US 27 | Ratings & Feedback System | Feedback System | 1 | Restaurant Developer | restaurant-system | 2026-02-07 | 2026-02-07 | 6 | US 8 | Pending
| 28 | 5 | US 30 | Explore Feed of Trending Meetup Spots | Recommendations | 3 | Analytics Developer | analytics-system | 2026-03-07 | 2026-04-07 | 10 | US 8 | Pending
| 29 | 5 | US 14 | Cuisine Preference Selection | Filtering and Preferences | 1 | Restaurant Developer | restaurant-system | 2026-05-07 | 2026-05-07 | 6 | US 8 | Pending
| 30 | 5 | US 2 | Dynamic Budget Split | Pricing and Payments | 1 | Backend Developer | backend-core | 2026-06-07 | 2026-06-07 | 8 | US 15 | Pending | 2026-08-07 | 2026-08-07

## Agile Sprint 1 Backlog
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORGINAL ESTIMATE (In Hours) | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
User Story #1 : Secure Login & User Identity Management | 2 |  | Done | 12 | 3 | 3 | 2.5 | 2.5 | 1 | 12
Frontend |  | Shreya Shakya | Done | 2 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 2
Backend |  | Bipul Maharjan, Ojash Shakya | Done | 3 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 3
Database |  | Gabyani Sharma | Done | 2 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 2
Testing |  | Kripa Adhikari | Done | 3 | 0.5 | 1 | 0.5 | 0.5 | 0.5 | 3
Validation |  | Aashish Bhattarai | Done | 2 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 2
User Story #9: Profile Management | 2 |  | Done | 12 | 2.5 | 3 | 3 | 2.5 | 1 | 12
Frontend |  | Ojash Shakya | Done | 2 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 2
Backend |  | Shreya Shakya, Bipul Maharjan | Done | 3 | 0.5 | 1 | 0.5 | 0.5 | 0.5 | 3
Database |  | Aashish Bhattarai | Done | 2 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 2
Testing |  | Gabyani Sharma | Done | 3 | 0.5 | 0.5 | 1 | 0.5 | 0.5 | 3
Validation |  | Kripa Adhikari | Done | 2 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 2
User Story #28 : Dark / Light Mode | 1 |  | Done | 6 | 0.5 | 2 | 2 | 1 | 0.5 | 6
Frontend |  | Bipul Maharjan | Done | 1 | 0.5 | 0.5 | 0 | 0 | 0 | 1
Backend |  | Gabyani Sharma, Aashish Bhattarai | Done | 1 | 0 | 0.5 | 0.5 | 0 | 0 | 1
Database |  | Shreya Shakya | Done | 1 | 0 | 0.5 | 0.5 | 0 | 0 | 1
Testing |  | Kripa Adhikari | Done | 2 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 2
Validation |  | Ojash Shakya | Done | 1 | 0 | 0 | 0.5 | 0.5 | 0 | 1
User Story #17 :Language Translation (English/Nepali) | 1 |  | Done | 6 | 0 | 0 | 1.5 | 3 | 1.5 | 6
Frontend |  | Kripa Adhikari | Done | 1 | 0 | 0 | 0.5 | 0.5 | 0 | 1
Backend |  | Bipul Maharjan, Shreya Shakya | Done | 2 | 0 | 0 | 0.5 | 1 | 0.5 | 2
Database |  | Aashish Bhattarai | Done | 1 | 0 | 0 | 0.5 | 0.5 | 0 | 1
Testing |  | Ojash Shakya | Done | 1 | 0 | 0 | 0 | 0.5 | 0.5 | 1
Validation |  | Gabyani Sharma | Done | 1 | 0 | 0 | 0 | 0.5 | 0.5 | 1
User Story #4:Emergency Alerts | 1 |  | Done | 6 | 0 | 0 | 0 | 3 | 3 | 6
Frontend |  | Gabyani Sharma | Done | 1 | 0 | 0 | 0 | 0.5 | 0.5 | 1
Backend |  | Ojash Shakya, Aashish Bhattarai | Done | 2 | 0 | 0 | 0 | 1 | 1 | 2
Database |  | Kripa Adhikari | Done | 1 | 0 | 0 | 0 | 0.5 | 0.5 | 1
Testing |  | Shreya Shakya | Done | 1 | 0 | 0 | 0 | 0.5 | 0.5 | 1
Validation |  | Bipul Maharjan | Done | 1 | 0 | 0 | 0 | 0.5 | 0.5 | 1
User Story #26:Friend Availability Scheduler | 1 |  | Done | 6 | 0 | 0 | 0 | 3 | 3 | 6
Frontend |  | Aashish Bhattarai | Done | 1 | 0 | 0 | 0 | 0.5 | 0.5 | 1
Backend |  | Gabyani Sharma, Kripa Adhikari | Done | 2 | 0 | 0 | 0 | 1 | 1 | 2
Database |  | Bipul Maharjan | Done | 1 | 0 | 0 | 0 | 0.5 | 0.5 | 1
Testing |  | Ojash Shakya | Done | 1 | 0 | 0 | 0 | 0.5 | 0.5 | 1
Validation |  | Shreya Shakya | Done | 1 | 0 | 0 | 0 | 0.5 | 0.5 | 1
TOTAL | 8 |  |  | 48 | 6 | 8 | 9 | 15 | 10 | 48
IDEAL |  |  |  | 48 | -3.6 | -1.6 | -0.6 | 5.4 | 0.4 | 48

## Agile Sprint 2 Backlog
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORGINAL ESTIMATE (In Hours) | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
User Story #7 :Midpoint Meeting Calculator | 3 |  | Done | 14 | 3 | 3 | 3 | 4 | 2 | 15
Frontend |  | Shreya Shakya | Done |  | 2 | 1 | 0 | 0 | 0 | 3
Backend |  | Bipul Maharjan, Ojash Shakya | Done |  | 1 | 1 | 1 | 0 | 0 | 3
Database |  | Gabyani Sharma | Done |  | 0 | 1 | 1 | 1 | 0 | 3
Testing |  | Kripa Adhikari | Done |  | 0 | 0 | 1 | 2 | 0 | 3
Validation |  | Aashish Bhattarai | Done |  | 0 | 0 | 0 | 1 | 2 | 3
User Story #8 :Nearby Restaurant Recommendation | 1 |  | Done | 5 | 1 | 1.5 | 1 | 1 | 0 | 4.5
Frontend |  | Ojash Shakya | Done |  | 1 | 0.5 | 0 | 0 | 0 | 1.5
Backend |  | Shreya Shakya, Bipul Maharjan | Done |  | 0 | 1 | 0.5 | 0 | 0 | 1.5
Database |  | Aashish Bhattarai | Done |  | 0 | 0 | 0.5 | 0.5 | 0 | 1
Testing |  | Gabyani Sharma | Done |  | 0 | 0 | 0 | 0.5 | 0 | 0.5
Validation |  | Kripa Adhikari | Done |  | 0 | 0 | 0 | 0 | 0 | 0
User Story #15 :Budget-Based Restaurant Filter | 1 |  | Done | 5 | 1 | 1.5 | 1 | 1 | 0.5 | 5
Frontend |  | Bipul Maharjan | Done |  | 1 | 0.5 | 0 | 0 | 0 | 1.5
Backend |  | Gabyani Sharma, Aashish Bhattarai | Done |  | 0 | 1 | 0.5 | 0 | 0.5 | 2
Database |  | Shreya Shakya | Done |  | 0 | 0 | 0.5 | 0.5 | 0 | 1
Testing |  | Kripa Adhikari | Done |  | 0 | 0 | 0 | 0.5 | 0 | 0.5
Validation |  | Ojash Shakya | Done |  | 0 | 0 | 0 | 0 | 0 | 0
User Story #11 :Ambience-Based Restaurant Filter | 2 |  | Done | 9 | 1 | 1 | 3 | 2 | 1 | 9
Frontend |  | Kripa Adhikari | Done |  | 1 | 1 | 0 | 0 | 0 | 2
Backend |  | Bipul Maharjan, Shreya Shakya | Done |  | 0 | 1 | 2 | 0 | 0 | 3
Database |  | Aashish Bhattarai | Done |  | 0 | 0 | 1 | 1 | 0 | 2
Testing |  | Ojash Shakya | Done |  | 0 | 0 | 0 | 1 | 0 | 1
Validation |  | Gabyani Sharma | Done |  | 0 | 0 | 0 | 0 | 1 | 1
User Story #13 :Restaurant Rating & Review Filter | 2 |  | Done | 9 |  | 1 | 1 |  | 4 | 0
Frontend |  | Gabyani Sharma | Done |  | 0 | 1 | 1 | 1 | 0 | 3
Backend |  | Ojash Shakya, Aashish Bhattarai | Done |  | 0 | 0 | 1 | 2 | 1 | 4
Database |  | Kripa Adhikari | Done |  | 0 | 0 | 0 | 1 | 1 | 2
Testing |  | Shreya Shakya | Done |  | 0 | 0 | 0 | 1 | 1 | 2
Validation |  | Bipul Maharjan | Done |  | 0 | 0 | 0 | 0 | 1 | 1
User Story #21 :Favourite Places Save Option | 1 |  | Done | 4 | 0 | 0 | 1 | 2.5 | 1 | 0
Frontend |  | Aashish Bhattarai | Done |  | 0 | 0 | 0.5 | 0.5 | 0 | 1
Backend |  | Gabyani Sharma, Kripa Adhikari | Done |  | 0 | 0 | 0.5 | 1 | 1 | 2.5
Database |  | Bipul Maharjan | Done |  | 0 | 0 | 0 | 0.5 | 0 | 0.5
Testing |  | Ojash Shakya | Done |  | 0 | 0 | 0 | 0.5 | 0 | 0.5
Validation |  | Shreya Shakya | Done |  | 0 | 0 | 0 | 0 | 0 | 0
TOTAL | 10 |  |  | 46 | 6 | 8 | 9 | 13 | 10 | 46
IDEAL |  |  |  | 46 | -3.2 | -1.2 | -0.2 | 3.8 | 0.8 | 46

## Agile Sprint 3 Backlog
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORGINAL ESTIMATE (In Hours) | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
User Story #3 : Ride Cost Estimation | 3 |  | Done | 14 | 4 | 3 | 3 | 2 | 2 | 14
Frontend |  | Shreya Shakya | Done | 2 | 1 | 0 | 0 | 0 | 1 | 2
Backend |  | Bipul Maharjan, Ojash Shakya | Done | 4 | 2 | 1 | 1 | 0 | 0 | 4
Database |  | Gabyani Sharma | Done | 2 | 1 | 1 | 0 | 0 | 0 | 2
Testing |  | Kripa Adhikari | Done | 2 | 0 | 1 | 1 | 0 | 0 | 2
Validation |  | Aashish Bhattarai | Done | 4 | 0 | 0 | 1 | 2 | 1 | 4
User Story #10 :Fare Drop Alert | 1 |  | Done | 5 | 1 | 0.5 | 1 | 0.5 | 2 | 5
Frontend |  | Ojash Shakya | Done | 1 | 0.5 | 0 | 0 | 0 | 0.5 | 1
Backend |  | Shreya Shakya, Bipul Maharjan | Done | 1 | 0.5 | 0 | 0 | 0 | 0.5 | 1
Database |  | Aashish Bhattarai | Done | 1 | 0 | 0.5 | 0.5 | 0 | 0 | 1
Testing |  | Gabyani Sharma | Done | 1 | 0 | 0 | 0.5 | 0.5 | 0 | 1
Validation |  | Kripa Adhikari | Done | 1 | 0 | 0 | 0 | 0 | 1 | 1
User Story #20 :Peak Hour Fare Warning | 1 |  | Done | 5 | 1 | 1 | 1 | 0.5 | 1.5 | 5
Frontend |  | Bipul Maharjan | Done | 1 | 0.5 | 0 | 0 | 0 | 0.5 | 1
Backend |  | Gabyani Sharma, Aashish Bhattarai | Done | 1 | 0.5 | 0.5 | 0 | 0 | 0 | 1
Database |  | Shreya Shakya | Done | 1 | 0 | 0.5 | 0.5 | 0 | 0 | 1
Testing |  | Kripa Adhikari | Done | 1 | 0 | 0 | 0.5 | 0.5 | 0 | 1
Validation |  | Ojash Shakya | Done | 1 | 0 | 0 | 0 | 0 | 1 | 1
User Story #16 : Walking Distance Calculator | 1 |  | Done | 9 | 2 | 2 | 3 | 1 | 1 | 9
Frontend |  | Kripa Adhikari | Done | 1 | 1 | 0 | 0 | 0 | 0 | 1
Backend |  | Bipul Maharjan, Shreya Shakya | Done | 3 | 1 | 1 | 1 | 0 | 0 | 3
Database |  | Aashish Bhattarai | Done | 2 | 0 | 1 | 1 | 0 | 0 | 2
Testing |  | Ojash Shakya | Done | 1 | 0 | 0 | 1 | 0 | 0 | 1
Validation |  | Gabyani Sharma | Done | 2 | 0 | 0 | 0 | 1 | 1 | 2
User Story #25 : Multi-Stop Route Planning | 3 |  | Done | 9 | 1 | 2 | 3 | 2 | 1 | 9
Frontend |  | Gabyani Sharma | Done | 2 | 1 | 1 | 0 | 0 | 0 | 2
Backend |  | Ojash Shakya, Aashish Bhattarai | Done | 3 | 0 | 1 | 1 | 1 | 0 | 3
Database |  | Kripa Adhikari | Done | 1 | 0 | 0 | 1 | 0 | 0 | 1
Testing |  | Shreya Shakya | Done | 1 | 0 | 0 | 1 | 0 | 0 | 1
Validation |  | Bipul Maharjan | Done | 2 | 0 | 0 | 0 | 1 | 1 | 2
User Story #23:Restaurant Offers Check | 1 |  | Done | 4 | 0 | 1 | 1.5 | 1.5 | 0 | 4
Frontend |  | Gabyani Sharma | Done | 1 | 0 | 0.5 | 0.5 | 0 | 0 | 1
Backend |  | Ojash Shakya, Aashish Bhattarai | Done | 1 | 0 | 0.5 | 0.5 | 0 | 0 | 1
Database |  | Kripa Adhikari | Done | 1 | 0 | 0 | 0.5 | 0.5 | 0 | 1
Testing |  | Shreya Shakya | Done | 1 | 0 | 0 | 0 | 1 | 0 | 1
Validation |  | Bipul Maharjan | Done | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL | 10 |  |  | 46 | 9 | 9.5 | 12.5 | 7.5 | 7.5 | 46
IDEAL |  |  |  | 46 | -0.2 | 0.3 | 3.3 | -1.7 | -1.7 | 46

## Agile Sprint 4 Backlog
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORGINAL ESTIMATE (In Hours) | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
User Story #6 :Group Voting Place | 2 |  | Done | 13 | 3 | 3 | 2.5 | 3.5 | 1 | 13
Frontend |  | Shreya Shakya | Done | 2 | 1 | 0.5 | 0.5 | 0 | 0 | 2
Backend |  | Bipul Maharjan, Ojash Shakya | Done | 5 | 1 | 1 | 1 | 2 | 0 | 5
Database |  | Gabyani Sharma | Done | 2 | 1 | 0.5 | 0 | 0.5 | 0 | 2
Testing |  | Kripa Adhikari | Done | 2 | 0 | 1 | 0.5 | 0.5 | 0 | 2
Validation |  | Aashish Bhattarai | Done | 2 | 0 | 0 | 0.5 | 0.5 | 1 | 2
User Story #12 : Group Chat for Meetup Planning | 3 |  | Done | 12 | 2.5 | 3 | 3 | 2.5 | 1 | 12
Frontend |  | Ojash Shakya | Done | 2 | 0.5 | 1 | 0.5 | 0 | 0 | 2
Backend |  | Shreya Shakya, Bipul Maharjan | Done | 4 | 1 | 1 | 1 | 0.5 | 0.5 | 4
Database |  | Aashish Bhattarai | Done | 2 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 2
Testing |  | Gabyani Sharma | Done | 2 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 2
Validation |  | Kripa Adhikari | Done | 2 | 0 | 0 | 0.5 | 1 | 0.5 | 2
User Story #5 : Meeting Reminder | 1 |  | Done | 4 | 0 | 0.5 | 1 | 1.5 | 1 | 4
Frontend |  | Bipul Maharjan | Done | 1 | 0 | 0.5 | 0.5 | 0 | 0 | 1
Backend |  | Gabyani Sharma, Aashish Bhattarai | Done | 1 | 0 | 0 | 0.5 | 0.5 | 0 | 1
Database |  | Shreya Shakya | Done | 1 | 0 | 0 | 0 | 0.5 | 0.5 | 1
Testing |  | Kripa Adhikari | Done | 0.5 | 0 | 0 | 0 | 0.5 | 0 | 0.5
Validation |  | Ojash Shakya | Done | 0.5 | 0 | 0 | 0 | 0 | 0.5 | 0.5
User Story #22 : Smart Notification Alerts | 2 |  | Done | 4 | 0.5 | 0.5 | 1 | 1 | 1 | 4
Frontend |  | Kripa Adhikari | Done | 1 | 0.5 | 0.5 | 0 | 0 | 0 | 1
Backend |  | Bipul Maharjan, Shreya Shakya | Done | 1 | 0 | 0 | 0.5 | 0.5 | 0 | 1
Database |  | Aashish Bhattarai | Done | 1 | 0 | 0 | 0.5 | 0.5 | 0 | 1
Testing |  | Ojash Shakya | Done | 0.5 | 0 | 0 | 0 | 0 | 0.5 | 0.5
Validation |  | Gabyani Sharma | Done | 0.5 | 0 | 0 | 0 | 0 | 0.5 | 0.5
User Story #29:Calendar Sync | 1 |  | Done | 14 | 3.5 | 3 | 3.5 | 2 | 2 | 14
Frontend |  | Gabyani Sharma | Done | 2 | 1 | 0.5 | 0.5 | 0 | 0 | 2
Backend |  | Ojash Shakya, Aashish Bhattarai | Done | 5 | 1 | 1 | 1 | 1 | 1 | 5
Database |  | Kripa Adhikari | Done | 3 | 1 | 1 | 0.5 | 0.5 | 0 | 3
Testing |  | Shreya Shakya | Done | 2 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 2
Validation |  | Bipul Maharjan | Done | 2 | 0 | 0 | 1 | 0 | 1 | 2
TOTAL | 9 |  |  | 47 | 9.5 | 10 | 11 | 10 | 6.5 | 47
IDEAL |  |  |  | 47 | 0.1 | 0.6 | 1.6 | 0.6 | -2.9 | 47

## Agile Sprint 5 Backlog
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORGINAL ESTIMATE (In Hours) | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
User Story #18 :Meetup Gallery | 1 |  | Done | 5 | 0.5 | 1 | 1.5 | 1 | 1 | 5
Frontend |  | Shreya Shakya | Done | 1.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 1.5
Backend |  | Bipul Maharjan, Ojash Shakya | Done | 1 | 0 | 0.5 | 0.5 | 0 | 0 | 1
Database |  | Gabyani Sharma | Done | 1 | 0 | 0 | 0.5 | 0.5 | 0 | 1
Testing |  | Kripa Adhikari | Done | 1 | 0 | 0 | 0 | 0.5 | 0.5 | 1
Validation |  | Aashish Bhattarai | Done | 0.5 | 0 | 0 | 0 | 0 | 0.5 | 0.5
User Story #19 :Achievement / Badge System | 1 |  | Done | 7 | 0.5 | 1.5 | 1.5 | 2 | 1.5 | 7
Frontend |  | Ojash Shakya | Done | 2 | 0.5 | 1 | 0.5 | 0 | 0 | 2
Backend |  | Shreya Shakya, Bipul Maharjan | Done | 2 | 0 | 0.5 | 0.5 | 1 | 0 | 2
Database |  | Aashish Bhattarai | Done | 1.5 | 0 | 0 | 0.5 | 0.5 | 0.5 | 1.5
Testing |  | Gabyani Sharma | Done | 1 | 0 | 0 | 0 | 0.5 | 0.5 | 1
Validation |  | Kripa Adhikari | Done | 0.5 | 0 | 0 | 0 | 0 | 0.5 | 0.5
User Story #24 :Meeting History & Analytics | 2 |  | Done | 10 | 1 | 2 | 2.5 | 2.5 | 2 | 10
Frontend |  | Bipul Maharjan | Done | 2.5 | 1 | 1 | 0.5 | 0 | 0 | 2.5
Backend |  | Gabyani Sharma, Aashish Bhattarai | Done | 2.5 | 0 | 1 | 1 | 0.5 | 0 | 2.5
Database |  | Shreya Shakya | Done | 2 | 0 | 0 | 1 | 1 | 0 | 2
Testing |  | Kripa Adhikari | Done | 1.5 | 0 | 0 | 0 | 1 | 0.5 | 1.5
Validation |  | Ojash Shakya | Done | 1.5 | 0 | 0 | 0 | 0 | 1.5 | 1.5
User Story #27 :Ratings & Feedback System | 1 |  | Done | 5 | 0.5 | 1 | 1 | 1.5 | 1 | 5
Frontend |  | Kripa Adhikari | Done | 1 | 0.5 | 0.5 | 0 | 0 | 0 | 1
Backend |  | Bipul Maharjan, Shreya Shakya | Done | 1.5 | 0 | 0.5 | 0.5 | 0.5 | 0 | 1.5
Database |  | Aashish Bhattarai | Done | 1 | 0 | 0 | 0.5 | 0.5 | 0 | 1
Testing |  | Ojash Shakya | Done | 1 | 0 | 0 | 0 | 0.5 | 0.5 | 1
Validation |  | Gabyani Sharma | Done | 0.5 | 0 | 0 | 0 | 0 | 0.5 | 0.5
User Story #30:Explore Feed of Trending Meetup Spots | 1 |  | Done | 8 | 1 | 2 | 1.5 | 2 | 1.5 | 8
Frontend |  | Gabyani Sharma | Done | 2 | 1 | 1 | 0 | 0 | 0 | 2
Backend |  | Ojash Shakya, Aashish Bhattarai | Done | 2 | 0 | 1 | 1 | 0 | 0 | 2
Database |  | Kripa Adhikari | Done | 1.5 | 0 | 0 | 0.5 | 1 | 0 | 1.5
Testing |  | Shreya Shakya | Done | 1.5 | 0 | 0 | 0 | 1 | 0.5 | 1.5
Validation |  | Bipul Maharjan | Done | 1 | 0 | 0 | 0 | 0 | 1 | 1
User Story #14:Cuisine Preference Selection | 1 |  | Done | 5 | 0.5 | 1 | 1 | 1.5 | 1 | 5
Frontend |  | Aashish Bhattarai | Done | 1 | 0.5 | 0.5 | 0 | 0 | 0 | 1
Backend |  | Gabyani Sharma, Kripa Adhikari | Done | 1.5 | 0 | 0.5 | 0.5 | 0.5 | 0 | 1.5
Database |  | Bipul Maharjan | Done | 1 | 0 | 0 | 0.5 | 0.5 | 0 | 1
Testing |  | Ojash Shakya | Done | 1 | 0 | 0 | 0 | 0.5 | 0.5 | 1
Validation |  | Shreya Shakya | Done | 0.5 | 0 | 0 | 0 | 0 | 0.5 | 0.5
User Story #2:Dynamic Budget Split | 1 |  | Done | 7 | 1 | 1.5 | 1 | 2 | 1.5 | 7
Frontend |  | Aashish Bhattarai | Done | 1.5 | 1 | 0.5 | 0 | 0 | 0 | 1.5
Backend |  | Gabyani Sharma, Kripa Adhikari | Done | 2 | 0 | 1 | 0.5 | 0.5 | 0 | 2
Database |  | Bipul Maharjan | Done | 1.5 | 0 | 0 | 0.5 | 0.5 | 0.5 | 1.5
Testing |  | Ojash Shakya | Done | 1.5 | 0 | 0 | 0 | 1 | 0.5 | 1.5
Validation |  | Shreya Shakya | Done | 0.5 | 0 | 0 | 0 | 0 | 0.5 | 0.5
TOTAL | 7 |  |  | 47 | 5 | 10 | 10 | 12.5 | 9.5 | 47
IDEAL |  |  |  | 47 | -4.4 | 0.6 | 0.6 | 3.1 | 0.1 | 47